## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
S1 | S1 | US-01 | Setup of project environment (JDK, Spring Boot, MySQL DB) | MUST HAVE | None | Archita Porov | 3- Completed
S1 | S1 | US-02 | Implement Task CRUD (Create, Read, Update, Delete) using Thymeleaf UI | MUST HAVE | US-01 | Archita Porov | 3- Completed
S1 | S1 | US-03 | Add validations and error handling for task input | SHOULD HAVE | US-02 | Archita Porov | 3- Completed
S1 | S1 | US-04 | Integrate MySQL database for task persistence | MUST HAVE | US-02 | Archita Porov | 3- Completed
S1 | S1 | US-05 | Convert application to REST controller and verify APIs using Postman | SHOULD HAVE | US-04 | Archita Porov | 3- Completed
S2 | S2 | US-01 | Add filters, keyword search, sorting, and pagination in UI | MUST HAVE | None | Archita Porov | 3- Completed
S2 | S2 | US-02 | Add enums (Status, Priority) and improve task view UI | SHOULD HAVE | None | Archita Porov | 3- Completed
S2 | S2 | US-03 | Implement unit testing for TaskService using JUnit and Mockito | SHOULD HAVE | None | Archita Porov | 3- Completed
S2 | S2 | US-04 | Add additional REST endpoints for overdue, upcoming, and due-today tasks | COULD HAVE | US-01 | Archita Porov | 3- Completed
S2 | S2 | US-05 | Integrate Swagger UI for API testing and documentation | MUST HAVE | US-04 | Archita Porov | 3- Completed
S3 | S3 | US-01 | Implement user authentication (login/logout functionality) | MUST HAVE | None | Archita Porov | 3- Completed
S3 | S3 | US-02 | Integrate email notification service | MUST HAVE | US-01 | Archita Porov | 3- Completed
S3 | S3 | US-03 | Incorporate session management for authenticated users | MUST HAVE | US-01 | Archita Porov | 3- Completed
S3 | S3 | US-04 | Add error handling and descriptive responses for session errors | SHOULD HAVE | US-03 | Archita Porov | 3- Completed
S3 | S3 | US-05 | Use Thymeleaf fragments and merge user-task entities for per-user tasks | SHOULD HAVE | US-01 | Archita Porov | 3- Completed
S3 | S3 | US-06 | Added Scheduler Class to provide automatic email reminder functionality. | SHOULD HAVE | US-02 | Archita Porov | 3- Completed
S4 | S4 | US-01 | Add BCryptPassword Encoder class to secure password storage and retrieval. | MUST HAVE | None | Archita Porov | 3- Completed
S4 | S4 | US-02 | Design a dashboard page for the application. | COULD HAVE | None | Archita Porov | 3- Completed
S4 | S4 | US-03 | Develop functionality for user profile and methods to update the same. | COULD HAVE | None | Archita Porov | 3- Completed
S4 | S4 | US-04 | Add Export to CSV feature | COULD HAVE | Node | Archita Porov | 3- Completed
Note on F1: ====== ID#AAABcShYZQo Sumeet Kumar Barua08 (2025-01-27 09:44:41) Mention the US ID(s) on which the user story depends.

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 115 | 100.5 | 17.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 1 BACKLOG
US-01 | T1.1 | Create Spring Boot project setup with dependencies | 2025-11-29 | 2025-11-29 | Archita Porov | Development | Completed | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-01 | T1.2 | Open project in IntelliJ and create packages (Controller, Service, Entity) | 2025-11-29 | 2025-11-29 | Archita Porov | Development | Completed | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-01 | T1.3 | Define basic MVC classes and test flow | 2025-11-30 | 2025-11-30 | Archita Porov | Development | Completed | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-02 | T2.1 | Define Task entity and TaskService | 2025-12-01 | 2025-12-01 | Archita Porov | Development | Completed | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-02 | T2.2 | Define TaskController and connect to service | 2025-12-01 | 2025-12-02 | Archita Porov | Development | Completed | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-02 | T2.3 | Create HTML pages to show task list | 2025-12-02 | 2025-12-02 | Archita Porov | Development | Completed | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-03 | T3.1 | Add validations to HTML forms | 2025-12-04 | 2025-12-04 | Archita Porov | Development | Completed | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-03 | T3.2 | Implement backend validation in Controller | 2025-12-04 | 2025-12-05 | Archita Porov | Development | Completed | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-04 | T4.1 | Create MySQL database and add connection properties | 2025-12-05 | 2025-12-05 | Archita Porov | Development | Completed | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-04 | T4.2 | Modify TaskService and create TaskRepository | 2025-12-06 | 2025-12-07 | Archita Porov | Development | Completed | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-04 | T4.3 | Update Controller to use database | 2025-12-07 | 2025-12-08 | Archita Porov | Development | Completed | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-05 | T5.1 | Convert Controller to REST | 2025-12-09 | 2025-12-09 | Archita Porov | Development | Completed | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-05 | T5.2 | Verify APIs via Postman | 2025-12-10 | 2025-12-10 | Archita Porov | Testing | Completed | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 2 BACKLOG
US-01 | T1.1 | Add “View Task” button with popup UI | 2025-12-15 | 2025-12-15 | Archita Porov | Development | Completed | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-01 | T1.2 | Implement keyword-based search in task list | 2025-12-16 | 2025-12-16 | Archita Porov | Development | Completed | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-01 | T1.3 | Add pagination to task list | 2025-12-17 | 2025-12-17 | Archita Porov | Development | Completed | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-02 | T2.1 | Convert Status and Priority to Enums | 2025-12-18 | 2025-12-19 | Archita Porov | Development | Completed | 4 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-02 | T2.2 | Update UI and controller to support Enums | 2025-12-19 | 2025-12-19 | Archita Porov | Development | Completed | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-03 | T3.1 | Unit Test: getAllTasks and findById methods | 2025-12-20 | 2025-12-20 | Archita Porov | Testing | Completed | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-03 | T3.2 | Unit Test: addTask, updateTask, deleteTask | 2025-12-21 | 2025-12-21 | Archita Porov | Testing | Completed | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-03 | T3.3 | Unit Test: markTask (success, not found, already completed) | 2025-12-22 | 2025-12-22 | Archita Porov | Testing | Completed | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-03 | T3.4 | Unit Test: overdue, upcoming, due-today tasks | 2025-12-22 | 2025-12-23 | Archita Porov | Testing | Completed | 3 | 1.5 | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-04 | T4.1 | Create REST endpoints for overdue, upcoming, due-today tasks | 2025-12-23 | 2025-12-23 | Archita Porov | Development | Completed | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-05 | T5.1 | Integrate Swagger UI for API testing | 2025-12-24 | 2025-12-24 | Archita Porov | Development | Completed | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-05 | T5.2 | Define and describe APIs (add endpoint descriptions, parameters, responses) | 2025-12-25 | 2025-12-25 | Archita Porov | Development | Completed | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 3 BACKLOG
US-01 | T1.1 | Create User entity and authentication service | 2025-12-29 | 2025-12-29 | Archita Porov | Development | Completed | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-01 | T1.2 | Design login/logout HTML pages and connect endpoints | 2025-12-30 | 2025-12-30 | Archita Porov | Development | Completed | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-02 | T2.1 | Add email API dependencies and configure properties | 2025-12-30 | 2025-12-30 | Archita Porov | Development | Completed | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-02 | T2.2 | Create EmailService class and methods | 2025-12-31 | 2026-01-01 | Archita Porov | Development | Completed | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-02 | T2.3 | Test email functionality in the application | 2026-01-02 | 2026-01-02 | Archita Porov | Testing | Completed | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-03 | T3.1 | Implement session handling for user login | 2026-01-05 | 2026-01-05 | Archita Porov | Development | Completed | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-03 | T3.2 | Update Controller endpoints to manage sessions | 2026-01-05 | 2026-01-05 | Archita Porov | Development | Completed | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-04 | T4.1 | Add error handling for session management | 2026-01-06 | 2026-01-06 | Archita Porov | Development | Completed | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-04 | T4.2 | Test and verify descriptive error pages | 2026-01-06 | 2026-01-06 | Archita Porov | Testing | Completed | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-05 | T5.1 | Define Thymeleaf fragments for reusable components | 2026-01-07 | 2026-01-07 | Archita Porov | Development | Completed | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-05 | T5.2 | Implement fragments (header, footer) in main pages | 2026-01-07 | 2026-01-07 | Archita Porov | Development | Completed | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-05 | T5.3 | Merge User and Task entities for per-user tasks | 2026-01-08 | 2026-01-08 | Archita Porov | Development | Completed | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-06 | T6.1 | Create Scheduler class and define methods. | 2026-01-09 | 2026-01-09 | Archita Porov | Development | Completed | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-06 | T6.2 | Update UI to add reminder functionality. | 2026-01-09 | 2026-01-10 | Archita Porov | Development | Completed | 3 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 4 BACKLOG
US-01 | T1.1 | Create SecurityConfig class and update methods in user service to hash passwords. | 2026-01-13 | 2026-01-13 | Archita Porov | Development | Completed | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-02 | T2.1 | Create Dashboard controller and define API to get statistics. | 2026-01-13 | 2026-01-14 | Archita Porov | Development | Completed | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-02 | T2.2 | Create html pages to fetch data from controller. | 2026-01-16 | 2026-01-17 | Archita Porov | Development | Completed | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-02 | T2.3 | Design the CSS for the dashboard style. | 2026-01-16 | 2026-01-18 | Archita Porov | Development | Completed | 5 | 2 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-03 | T3.1 | Create Controller and design API endpoints for user profile. | 2026-01-14 | 2026-01-14 | Archita Porov | Development | Completed | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-03 | T3.2 | Create html pages for user profile displays. | 2026-01-15 | 2026-01-16 | Archita Porov | Development | Completed | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-03 | T3.3 | Design CSS for user pages. | 2026-01-15 | 2026-01-16 | Archita Porov | Development | Completed | 4 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-04 | T4.1 | Create controller endpoint and functions to export tasks to CSV | 2026-01-19 | 2026-01-19 | Archita Porov | Development | Completed | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-04 | T4.2 | Define html interface for users to use the functionality. | 2026-01-19 | 2026-01-19 | Archita Porov | Development | Completed | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-04 | T4.3 | Enchance the function by providing mailing feature | 2026-01-19 | 2026-01-20 | Archita Porov | Development | Completed | 3 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Note on D2: ====== ID#AAABcShYZRI Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on E2: ====== ID#AAABcShYZRU Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on I3: ====== ID#AAABcShYZQ4 Sumeet Kumar Barua08 (2025-01-27 09:44:41) This is the total task estimated in hours for all the user stories
Note on J3: ====== ID#AAABcShYZRc Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 1 work
Note on K3: ====== ID#AAABcShYZRg Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 2 work
Note on L3: ====== ID#AAABcShYZQs Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 3 work
Note on M3: ====== ID#AAABcShYZRo Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 4 work
Note on N3: ====== ID#AAABcShYZQw Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 5 work
Note on O3: ====== ID#AAABcShYZRk Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 6 work
Note on P3: ====== ID#AAABcShYZRY Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 7 work
Note on Q3: ====== ID#AAABcShYZRA Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 8 work
Note on R3: ====== ID#AAABcShYZRs Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 9 work
Note on S3: ====== ID#AAABcShYZRM Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 10 work
Note on T3: ====== ID#AAABcShYZRE Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 11 work
Note on U3: ====== ID#AAABcShYZQ8 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 12 work
Note on V3: ====== ID#AAABcShYZQ0 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 13 work
Note on W3: ====== ID#AAABcShYZRQ Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 14 work

## Stand up Meeting
Sprint | Day | Impediments | Action Taken
S1 | 2025-11-29 | Difficulty in identifying APIs and distinguishing MVC components | Studied Spring MVC architecture and structured Controller, Service, and Entity layers
S1 | 2025-12-01 | Whitelabel error due to incorrect controller endpoint definitions | Corrected controller mappings and verified MVC workflow
S1 | 2025-12-02 | Auto-increment logic for task IDs | Implemented auto ID generation logic in TaskService
S1 | 2025-12-03 | Whitelabel error due to link mismatch and GitHub push issues | Fixed link mappings and successfully pushed code to GitHub
S1 | 2025-12-04 | Difficulty defining validation patterns and due date limits | Implemented appropriate regex patterns and date validations
S1 | 2025-12-05 | Refactoring TaskService for MySQL integration | Modified service and controller logic to support database operations
S1 | 2025-12-08 | Preventing users from manipulating task completion status | Restricted status updates through controlled controller logic
S1 | 2025-12-09 | Understanding REST controller response handling | Rebuilt controller as REST controller and tested endpoints
S1 | 2025-12-10 | Understanding pagination and filtering repository methods | Implemented paging and filter methods and updated UI
S1 | 2025-12-11 | No major impediments | Conducted retrospective and applied minor CSS enhancements
S2 | 2025-12-12 | Ensuring validation consistency across frontend and backend | Added validations and enhanced codebase
S2 | 2025-12-15 | UI misalignment while displaying task popup | Fixed HTML structure and popup styling
S2 | 2025-12-16 | Enum mismatches causing Whitelabel errors | Standardized enum values across codebase
S2 | 2025-12-17 | No major impediments | Implemented keyword-based search functionality
S2 | 2025-12-18 | Pagination UI issues during navigation | Fixed pagination logic and UI alignment
S2 | 2025-12-19 | No major impediments | Performed minor CSS adjustments
S2 | 2025-12-22 | Mockito instance mismatch during unit testing | Corrected mocking logic and fixed test cases
S2 | 2025-12-23 | Filtering tasks by date and status | Added repository-level date filtering and tested APIs
S2 | 2025-12-24 | Understanding Swagger API documentation features | Configured Swagger annotations and verified APIs
S2 | 2025-12-26 | No major impediments | Conducted sprint retrospective
S3 | 2025-12-29 | Whitelabel errors during login/logout API design | Corrected authentication endpoints
S3 | 2025-12-30 | Understanding email API configuration and app passwords | Configured email properties and tested email service
S3 | 2026-01-02 | No major impediments | Revised and validated email functionality
S3 | 2026-01-05 | Missing session-related endpoints | Implemented session handling and updated controllers
S3 | 2026-01-06 | Identifying multiple session error scenarios | Added try-catch blocks and fallback error handling
S3 | 2026-01-07 | CSS misalignment due to Thymeleaf fragments | Refactored fragments and fixed layout issues
S3 | 2026-01-08 | Entity-function mismatches while merging User and Task | Corrected entity mappings and repository logic
S3 | 2026-01-09 | DateTime issues while incorporating reminder functionality. | Defining common timezones to save consistent time related data values.
S4 | 2026-01-12 | No major impediments | Conducted retrospective and applied minor CSS enhancements
S4 | 2026-01-13 | Issues while migrating previously saved passwords. | Created separate methods to hash already stored passwords for testing.
S4 | 2026-01-16 | Designing the dashboard and collecting stats related data. | Define APIs providing statistical data rather than pre-populated pages.
S4 | 2026-01-19 | CSV data mishandling due to commas in description. | Use of escape sequences to resolve the issue.
S4 | 2026-01-20 | No major impediments | Conducted Major project discussions.
S4 | 2026-01-21 | No major impediments | Discussed project related documentations.
S4 | 2026-01-22 | No major impediments | Added MIT License to the project.

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1 | S1 | 2025-11-29 | 2025-12-11 | Archita Porov | Start planning controller endpoints before implementation | Stop fixing issues without reviewing logs | Continue following MVC best practices | Improved endpoint mapping and validation strategy
2 | S2 | 2025-12-12 | 2056-12-26 | Archita Porov | Start writing unit tests alongside feature development | Stop delaying UI testing until final stages | Continue improving code modularity | Added unit tests, improved UI stability, and refactored code
3 | S3 | 2025-12-29 | 2026-01-08 | Archita Porov | Start validating session and auth flows early | Stop hardcoding values in authentication logic | Continue using reusable UI components | Improved session handling, error pages, and entity relationships
4 | S4 | 2026-01-12 | 2026-01-25 | Archita Porov | Start defining APIs clearly before dashboard implementation | Stop assuming existing data formats will work for exports | Continue improving security and UI incrementally | Implemented BCrypt password hashing, resolved CSV export issues, improved dashboard design, added MIT License, and refined APIs for statistical data
5
6
7